## Sheet1
Jobs/Tasks to be done during YM 2021 | Updated 11/05/2021
This is a combined listing of all jobs/tasks to be done by Local Arrangements Committee (LAC) and helpers during the time of Prepartion Day and Yearly Meeting 13th to 17th May. Many thanks to all helpers
Times and Tasks | Group | Who
Thursday 13th May (Preparation Day) From 12 noon | LAC | All meet at venue just before 12 noon
Set up Registration Desk | LAC | Anne/Alistair
Signage - large directional signs and banners | LAC | Deb
Signage - smaller signs | LAC | Anne
Accommodation signs Put on inside of doors to Unit | LAC | Anne/Patricia
Deliver bedding sets to rooms in Units | LAC | ?
Sort food for teas & label. Make instructions for teas | LAC | Alistair
Set up sound/Zoom not needed till Fri arvo) | LAC | Alistair/Graham
Transport pick ups | Helpers | Deb looking after and OK for helpers
Set up Elm Hall for Preparation Day | LAC | Jude needs seats in horseshoe facing whiteboard. Tables only needed Thurs evening session
Registration Desk open 1 pm till 2.30 pm
Welcoming people as they arrive | Helpers | Alistair and Patricia
Helping at Registration Desk/Taking people to rooms | LAC/Helpers | Alistair and Patricia
Preparation Day sessions starts at 2 pm
Welcome | LAC - PNMM | Michael Short
Welcome from venue, health and safety | Venue person
Hosuekeeping notices | LAC | Anne
Afternoon tea times 3.30pm - 4 pm | LAC/Helpers | Anne to do afternoon tea
Supper/supper clean up | LAC | Anne/Alistair
Lock up/open up next am | LAC | Anne/Alistair
Friday 14th May (Preparation Day) until 12.15pm
Morning tea time 10.30am - 11 am | LAC/Helpers | Anne to do morning tea
Transport pick ups | Helpers | Deb arranging. Has people arrriving Fri 10 am - alert them re lunch Fri
At end of Prep Day
Tidy/set up Elm Hall for Pastoral & Spiritual Care Meeting. Need a whiteboard. Check with Elizabeth Duke re layout | LAC | Michael
Put up signs for Fri arvo meetings. Pastoral Care in Elm Hall, Standing Cttee in Elm Lodge Lounge, Trust Board in Unit 5 | LAC | Anne
Make sure Zoom is set up in Elm Hall | LAC | Alistair/Graham
Friday 14th May. Friday afternoon/Meetings
Registration Desk 1 pm - 5.30 pm and 6.30pm - 7.30 pm
Welcoming people/directions to meeting rooms | Helpers | Anne Hall 1 - 5.30 pm. Michael 3.30 pn -
Help at Registration Desk/Taking people to accommodation | Helpers/LAC | Viola plus will have Deb's phone while Deb at Trust Board
Transport pick ups | Helpers | Deb has Juliet and Jocelyn to help. They may also help at Rego Desk
Afternoon tea 3 pm - 4 pm | LAC/helpers | Anne/Viola people on Registration Desk
After meetings tidy spaces/change or remove signs | LAC | Anne - signs
Friday 14th May Friday evening YM session 7 pm
Welcome from LAC - KMM | LAC | Graham Chapman
Housekeeping from LAC | LAC | Anne
(Also be Venue welcome - about 7.30 pm) | Venue
Supper/supper clean up | LAC | Anne/Alistair
Lock up/open up in am | LAC | Anne/Alistair
Saturday 15th May YM in session 9.am onwards
Registration Desk times 8.30 am - 9.30 am
Help at Rego Desk/Welcomes | LAC/Helpers | Michael
Notices | LAC | Anne/Michael
Morning tea 10.30am - 11am | Helpers/LAC | Michael plus Need a volunteer
Photograph 3 pm | LAC | Deb
Afternoon tea 3.30 - 4 pm | Helpers/LAC | Michael/Viola
At close of afternoon 5.15 pm - lock up Elm Hall |  | Alistair/Anne
Saturday 15th May Quaker Lecture 7 pm
Support people for Lecturer -Anjum |  | Jim Flewitt and Patricia
Set up - stage dressing | KMM | Deb and Alison
Sound system/Zoom set up | LAC | Alistair/Graham
Lecturn, table and chairs on stage | LAC arrange with venue | Deb/via form
Seating in Kauri Hall | LAC arrange with venue | Deb/via form
Tea set up in Elm Dining | LAC | Anne (take herb teas/non dairy milk from Fireside plus fruit, plates?) throws
Booklet sales set up - get from Jim Flewitt, float from Anne. Have booklets in Kauri Hall and later move to Elm Dining. Booklet sales people | LAC | Michael and Cathee Glennon
Signs - put out/banners ... | LAC | Anne
Person in carpark to direct people | Helpers | Garry Buckman (PNMM) need another volunteer
Welcomers at door | LAC/Helpers | Viola and Vincent
Outreach pamphlets | From Outreach Ctte(Jan Schmidt) | Have close to lecture booklets in Kauri Hall and move to Elm Dining
Help with tea | LAC/Helpers | To ask for volunteers at YM
Tidy up, remove signs/banners and lock up spaces | LAC/Helpers | Anne/Al for lock up Kauri Hall and Elm Dining
Move sound and zoom gear back to Elm Hall |  | Alistair/Graham Deb will also be about
Sunday 16th May YM in session 9 am onwards
Registration Desk times 8.30 am - 9.30 am. Only person for Sunday arriving in pm. May not need this slot
Help at Rego Desk/Welcomes | LAC/Helpers | Michael
Set up sign up sheet for rides on Monday | LAC | Anne
Notices | LAC | Anne/Michael
Morning tea 10.30am - 11 am | Helpers/LAC | Cathee Glennon + - may need a volunteer
Afternoon tea 3pm - 3.30 pm | Helpers/LAC | Patricia and will need a volunteer
Supper/supper clean up | LAC | Anne/Alistair
Lock up/open up am | LAC | Anne/Alistair
Monday 17th May YM in session 9 am till 12.30pm
Registration Desk times - none - have sign out to say people about over morning tea
Transport drop offs/offers for rides. On sign up sheet |  | Deb to check what still needs sorting. Helpers, Viola
Notices | LAC | Anne/Michael
Morning tea 10.30am - 11 am | Helpers/LAC | Cathee and Vicki? Plus Deb
Tidy up spaces | LAC
Remove all signage | LAC
Remove all equipment/displays etc. | LAC
Return keys | LAC