## Checklist
YM ?? Checklist
Updated At 09/05/2021
timing | SITE – in general | Who is to do this | Date when done | Notes
At least one year in advance | Book site (1)
From booking till YM | - Liaise with site
During YM | - Liaise with site person
| Site person at first session |  |  | Welcome and health and safety
Pre YM | Access to venue
Signage for event done by the venue
Liaise with venue re general signage for YM event.
| Get site map |  | Done | Make copies for Registration packs
Main room
Site visit | - Check electronic equipment
Site visit | - Check for microphones (2)
Site visit | Check wifi in room
Site visit | Check connection to sound system
Site visit | Check out using camera and sound etc for Zoom if offering zoom
4 months before | Find a tech person or persons
Site visit | Have dedicated computer for connecting to data projector. Check connections. Can use a "pointer" ? |  |  | Note YM has data projector lives at Settlement
Data projectors check if needed plus specific requirements for all presenters in person and via zoom (what features they wish to use)
Site visit | Access for wheelchair - check can small ramps be added raound doorways?
Site visit | - Check that the required number of seats are available |  |  | On site visit checked 100 seats
| Check items in other meeting rooms - whiteboard, lecturns ... |  |  | Checked in site visit
| Check tables available for displays, for Prep Day, small table for data projector (if needed) small table in main meeting room for Faith and Practice |  |  | Checked in site visit
After site visit | - hire furniture (If needed) | Not needed
Day before YM | - transport furniture (If hired)-check with hire Co | Not needed
End YM | - return furniture (If hired) | Not needed
Day before YM | COVID poster and sign in sheet, hand sanitiser | Event COVID poster |  | Have a sign up book and hand sanitiser
Day before YM | - Set out room | LAC
End YM | - Tidy room up | LAC
Microphones
Site visit | - what needs to be hired |  |  | Need 1 corded/fixed, plus 2 wireless
2 months ahead or before | - hire microphones
- day before pick up
End YM | - return hired gear
Accommodation
Site visit | - Get map of lay out from site people |  |  | Check wheelchair access/bathrooms. Dining space, main meeting rooms.
1 week ahead | - Have a list of those staying
1 week ahead | - Allocate bedrooms
Site visit plus1 week ahead | Make signs - accommodation, venues for meetings, venue for prep day | Discuss and check during site visit. List of signs made after site visit
Day before YM | - Put up signs | LAC
Last day of YM | - collect signs | LAC
Site visit | - check parking
Food
On booking | - check cook is able to cater for vegetarians and other requirements
From booking till YM | - liaise with cook
2 days before YM | - list of numbers for meals
During YM | liaise with cook and special diets - they may need detailed information. Have a food liaison person
2 months before | What is required for meal clean up e.g do we need to wipe tables, vacum floor? Yes, wipe tables, take dishes to trolley
Morning & Afternoon tea etc.
Check set up during site visit | Morning & Afternoon tea etc. Check what venue is doing and what else is needed |  |  | Do need to provide herb/fruit teas??
I month before | Roster of helpers for set up, tidy up. ??? to do instructions
During YM | Liaise with venue if needed
Finances (4)
On booking | - find the site costs (3)
asap | - find a treasurer for the event
asap | - work out a budget (aim for a self-funding event)
asap | - work out how much to ask of those coming
asap | - set up a bank account [Yearly Meeting (year)}
asap | - get receipt book and work out how accounts are to be kept |  |  | Have receipt book. So far emailing back to confirm payment and rego details
When possible | - banking | internet banking |  | Only 4 cheques to bank in 2021
End of YM | - pay site
When possible | - pay other bills associated with YM
After YM | - finalise accounts
What is deal if we need to cancel due to COVID 19, including parts of NZ at different Levels?
Quaker books
4 months before | - liaise with Quaker Book Sales re a table of their books
4 months before | - find someone to be in charge of this table
Start of YM | - set out books
End of YM | - pack display up
Display room
Day before | - set room up from what YM Clerk has found out re how much space is required |  |  | Allow for more to cope with late requests for space
End YM | - make sure displays are packed up
End of YM | - return room to how it was
Registration Form (5)
| -Develop form | LAC |  | Create Event for YM on Website and make public. Add information/links to registration form to the event
5 months before | - online | LAC
5 months before | - paper | LAC
Information Sheet (6)
5 months before | - prepare this | LAC
Returned registration forms
5 months before | - construct database
Till YM | - Put info onto data base
Anytime | - Let YM clerk know those coming when asked
Anytime | - Let people have info when they require it
2 months before | Create information packs to send to all who have registered. If Zoom - they need a separate info pack
3 weeks before | Send info pack to those registered in person
! Week before? | Email Gold Papers to those registered for Zoom | YM Clerk will do this |  | Send list of those registered with email addresses to YM Clerk for emailing out
In week before | Print copies of Gold papers | LAC |  | Arrange with local printer. Get number registered for YM plus 10 copies
Advertising YM
2 issues before YM | - information sheet and registration form in the ANZ Friends Newsletter
2 months before | send around to worship groups |  |  | Info also went out in YM Clerks letter, Feb, Mar Apr 2021
5 months before | put on Quaker website with Yearly Meeting event. Need to have edit access - ask Website Technical Team for access
Registration Table & pre YM work
| Registration Desk times | LAC to decide |  | From 1 pm Thurs afternoon?? , from 1 pm Friday afternoon ?? Depending on venue and access times
2 weeks before | Name tags – get equipment or make |  |  | Borrowed plastic name tag holders from Settlement
2 weeks before | - either prepare name tags or have equipment available on the registration table
Day before YM | Set up table |  |  | Provide folder of helpful information for those doing slot at Registration Desk
2 months before | Roster of those to be at Registration Desk, especially on Fri afternoon
1 week before | COVID event poster with QR code, plus sign in book at rego desk
1 week before | Have to give to participants – map of place
1 week before | - info about their room
1 week before | - name tag
Few days before | gold papers
During YM | Have boxes for notices, lost property, epistle ideas, paper recycling
During YM | Housekeeping notices | LAC |  | Have box at Regn Desk. Check with YM Clerk for a daily slot for notices
Transport
- roster for transport pick up
Information as to who needs rides
2weeks before | n prepare
2 months before | n get volunteers
- roster for transport departure
During YM | n prepare |  |  | Put out sign up sheet
2 months before | n get volunteers
anytime | Liaise with YM Clerk |  |  | Note any AWPS visitors by Zoom. Australian person joining by Zoom Any presenters and their detailed requirement
Quaker Lecture
2 years before YM | QL committee and YM clerk liaise re lecture topic and possible lecturer
At least 6 months before | Find a site, if not part of the YM site |  |  | Good to have at same venue if possible, other wise will need to arrange transport
At least 6 months before | Book site
All the time | Liaise with QL committee
never | Liaise with Q Lecturer
Check equipment
Sound system
Site visit | - no. of seats
Site visit | - tables |  |  | Need small table on stage with at least 3 chairs
Site visit | microphones (for lecturer and roving one for questions) |  |  | Check with site visit for tech stuff. Might need wireless mic? Liaise with QLC.
Site visit | Live stream or zoom connection - yes be good is response from QLC |  |  | Check what technology and support staff needed/if this is possible?
Site visit | - lectern
Staging
- hire microphones (if need be)
During YM | Large leafy/floral arrangement for stage
During YM | Any security issues for QL - depends on lecturer/topic | LAC/QLC |  | If needed have a plan
Get volunteers (8) - to roster for jobs below (may be able to ask for help from those attending YM
1 month before | - to bake
1 month before | to welcome people at door
1 month before | - to do cuppa (if need be)
1 month before | - to wash up (if need be)
1 month before | to staff table for sale of booklets and to give out Quakers in Aotearoa or outreach pamphlets
1 week before | n organise float
After QL | n bank money
1 month before | Organise accommodation for lecturer if required
Publicity
4 months before | QL committee get poster done | QLC |  | QLC to do publicity - posters, fliers and national media.
2 months before | - amongst host MM Friends |  |  | Publicity opportunites in the local community and local Meetings
1-2 months before | - local |  |  | Ditto
Preparation Day
3 months before | Liaise with Facilitator re theme |  |  | Facilitator arrnaged with QLSD Committee
3 months before | Liaiase with facilitator re requirements for prep day sessions and timings
Beginning of session welcome from LAC, Welcome from venue, H and S, housekeeing
3 months before | Liaise with facilitator re Accommodation
3 months before | Liaise with facilitator re travel arrangements
On the day | Signage for the room
After prep day | Tidy room for next meeting. Change signage | LAC
Friday afternoon Meetings
3 months before | Liaise with YM Clerk re timing of meetings |  |  | Usually Pastoral Care meeting first followed by Standing Cttee
Liaise with QLSD who will facilitate Pastoral Care meeting. Check their requirements. Any who want to join via Zoom?
I week before | Allocate spaces for meetings | LAC |  | Pastoral etc care, Standing Committee
On the day | Signage for meeting spaces | LAC |  | To make with other signs
After meetings | Remove signage and tidy spaces ready for next meeting | LAC
3 months before | Liaise with Trust Board re meeting space. Note there may be requests from other Cttees/groups? |  |  | Allocate a space
JYFs joining YM ??

## Notes
Notes
(1) SITE requirements
· Seating for 100 in one room
· Separate room for Standing Committee
· Space for registration
· Space for displays
· Power points near clerk’s table
· Location near road/rail/air terminals
· Residential option
· Wheelchair accessible, preferably all on ground floor
· Separate dining room and kitchen
· Ability to self cater morning and afternoon teas
· Allow for rooms for Overseas visitors, as in 4 below.
(2) Microphones during YM
- 1 or 2 at clerks’ table
- 2 roving microphones
- Power box, etc
(3) Costs
- Cost for hiring rooms
- Costs of meals
- Costs of afternoon/morning tea
- Cost of day visitor
- Cost of use of bed
- Cost of use of linen
(4) What Yearly Meeting does
Yearly Meeting Clerk
- Sets agenda
- Liaises with AWPS visitor & makes sure they are registered (or done by FWCC reps)
- Liaises with Australia YM visitor & makes sure they are registered
Introduce the Quaker Lecturer
- Organises people to do things during YM
Yearly Meeting & money
- Deposit for site from YM treasurer – to be returned
- YM pays for AWPS visitor
- YM Pays for Australia YM visitor
- YM pays for YM Clerk
- YM pays for incoming YM Clerk
- YM pays for YM treasurer
- YM pays for Quaker Lecturer accommodation
- YM pays for hireage of hall for Quaker Lecture
- YM gives each MM the travel amounts for 2 people per MM which is then allocated by their Overseers
- YM receives any surplus or pays for any debt
(5) Registration form – what is on
- Name, address, phone numbers, email address
- Contact person while at YM
- Arrival time
- Departure time
- Need to be meet or not
- What accommodation required
- What meals required
- Cost for each day/meal/registration for YM
- When to return by
(6) Information Sheet to have on
- Dates of YM
- Name and address of venue
- Contact name, email address and phone number
- Info about accommodation
- Any other relevant points
(7) What Quaker lecture Committee does
- Communicates with Quaker Lecturer
Liaises with host MM
(8) Extra Volunteers may be needed for
- Money
- Preparing name tags
- Registration desk
- Transport
- Quaker Books
- Photographer
- QL front house
- QL booklet sales
- QL cuppa
- QL washing up
- QL baking
- QL roving microphone
Ask someone who has been to at least one YM as to how it is run so that the micromanagement is negated and you can focus on what YOU need to do.

## InTimeOrder
In Time Order
timing |  | Who is to do this | Date when done
2 years before YM | Host MM liaises with QL committee and YM clerk re lecture topic and possible lecturer
At least one year in advance | Book site(1)
On booking | Finances (4)
- find the site costs (3)
asap | - find a treasurer for the event
asap | - work out a budget (aim for a self-funding event)
asap | - work out how much to ask of those coming
asap | - set up a bank account [Yearly Meeting (year)}
asap | - get receipt book and work out how accounts are to be kept
-
On booking | - check cook is able to cater for vegetarians and other requirements
-
From booking till YM | - Liaise with site
- liaise with cook
All the time | Liaise with YM Clerk
Liaise with QL committee
Site visit | Main room
- Check electronic equipment
- Check for microphones (2)
- Check that the required number of seats are available
- what needs to be hired
- Get map of lay out from site people
- check parking
At least 9 months before | Find a site for QL, if not part of the YM site
Book site for QL
Site visit for QL | Check equipment
- no. of seats
- tables
- microphones (for lecturer and for questions)
- lectern
5 months before | Registration Form (5)
-Develop form
- online
- paper
Information Sheet (6)
- prepare this
2 issues before YM approx 5 months | - January of Yr – send dates to ANZ N/L to get into 1st issue
- information sheet and registration form in the ANZ Friends Newsletter
-
4 months before | - liaise with Quaker Book Sales re a table of their books
- find someone to be in charge of Q books table
- with help from QL committee get poster done
-
3 months before | - hire furniture (If needed)
-
2 months before | - hire microphones 4 YM (if needed)
- hire microphones (if needed) for QL
- send around worship groups info
Organise accommodation for lecturer if required
Publicity for QL
- amongst host MM Friends
- local
- share with QL committee so others can use
Roster of people
- to bake
- to do cuppa (if need be)
- to wash up (if need be)
- to staff table for sale of booklets and to give out Quakers in Aotearoa
2 weeks before | Name tags – get equipment
- either prepare name tags or have equipment available on the registration table
- prepare roster for transport pick up
1 wk ahead | - Have a list of those staying
- Allocate bedrooms
Have to give to participants – map of place
- info about their room
- name tag
Organise thank you for lecturer
n organise float QL
n organise float QL
-
2 days before YM | - list of numbers for meals
Day before YM | - Put up signs
Set up Registration Table
-
- gold papers put ready for Fds
- transport furniture (If needed)
- Set out room
Day before | - set display room up from what YM Clerk has found out re how much space is required
Start of YM | - set out books
-
During YM | - Liaise with site person
- liaise with cook
n prepare roster for transport departure
After QL | n bank money from sale of QL books
Last day of YM | - collect signs
-
End of YM | - return furniture (If needed)
-
- Tidy room up
- return hired gear
- pay site
- pack display up
- make sure displays are packed up
- return room to how it was
After YM | - finalise accounts
When possible | - banking
- pay bills assoc with YM